# Healthcare Guardian — Full Project Evaluation

Prepared by Woz | March 31, 2026

March 31, 2026

# Executive Summary

Healthcare Guardian is a legitimate B2B SaaS-adjacent business with a defensible market position, a real regulatory tailwind, and a well-built strategic foundation. The research, curriculum architecture, demo flow, and outreach sequences are all production-ready. The product has not yet generated revenue, but the infrastructure to do so exists. The primary gap is execution — specifically, the Phase 2 validation outreach has not started despite the plan being complete.

Overall assessment: Green. Execute. Correct one strategic error (geographic targeting). Fix the email sender problem. Move.

# Part 1: The Market

## Problem Scale

- Healthcare workers are ~10% of the U.S. workforce but absorb 48% of all nonfatal workplace violence injuries

- Healthcare workers are 5x more likely to experience workplace violence than the average U.S. worker

- WPV incidents increased 30% between 2021–2022

- 75% of all U.S. workplace assaults occur in healthcare and social service settings (OSHA)

- The American Hospital Association pegs total annual cost of WPV at $18.27 billion

- ED nurses report assault rates as high as 12.7 per 100 workers per year

- Reporting rates are estimated at 30–70% of actual incidents — cultural normalization is itself a correctable condition

## Regulatory Tailwinds

| Jurisdiction | Mandate | Status |
| --- | --- | --- |
| California | Cal/OSHA T8 §3342 + SB 553 (all employers, July 2024) | Active — most comprehensive in nation |
| New York | Hospital/nursing home WPV prevention law | Signed Dec. 2025 — effective September 2026 |
| Texas | HB 2025 — violence prevention plans for healthcare | Effective September 2024 |
| Illinois, WA, OR, NJ, CT | Active mandates or advanced legislation | Rolling |
| Joint Commission | New WPV prevention standards across behavioral health + home care | July 2024 — auditable, documentation required |

Federal OSHA rule is stalled (moved to Long-Term Action, September 2025). This actually helps: state-level mandates are accelerating to fill the void, creating a patchwork that makes a multi-state digital training product more valuable, not less.

New York’s September 2026 deadline is the single most urgent market activation in play right now.

## Competitive Landscape

| Provider | Focus | Weakness |
| --- | --- | --- |
| CPI (Crisis Prevention Institute) | De-escalation + restraint | $1,250–$3,450/person; restraint-heavy; slow to scale |
| AVADE Training | WPV prevention awareness | Compliance-focused; limited personal agency content |
| Vistelar | Communication-based prevention | Strong methodology; weak digital delivery |
| MOAB | Physical intervention | Very physical; liability-heavy |
| HealthStream / Relias | LMS catalog platforms | Generic; not specialized |
| MedTrainer | Compliance LMS | HIPAA/OSHA focused; not behavioral safety |

The gap: No competitor leads with individual behavioral agency — the concept that the employee, through awareness, positioning, communication, and decision-making, is the first and most powerful layer of their own defense. Healthcare Guardian owns that positioning if it executes.

# Part 2: Strategic Decisions Made

## The 7 Questions — Final Answers

Q1 — Physical Content Scope Exclude from digital product entirely for launch. Reserve for in-person curriculum (future upsell). Simplifies legal review, removes friction for risk managers, keeps digital product clean for enterprise compliance sales.

Q2 — Avatar Identity Female presenter, named Morgan Hayes. AI avatar via HeyGen. Nursing workforce is 87% female; same-gender pedagogical agents produce higher engagement and perceived credibility for self-advocacy content. Elias Reed remains the curriculum architect and brand voice in written/email communications — Morgan is the on-screen expert voice. Clean distinction.

Q3 — Launch Scope Single pilot module first (Module 3: Pattern Recognition, ~10–12 minutes), then full curriculum build. Price: $29/seat, minimum 5 seats ($145). Goal of pilot: proof of purchase, qualitative feedback, completion rate data — not revenue.

Q4 — Business Entity Healthcare Guardian LLC — Arizona filing (~$50–85 via azcc.gov). EIN via IRS.gov (free, 5 minutes). Business bank account (Mercury recommended). Stripe under entity. This must happen before any money moves.

Q5 — Pricing

| Tier | Price |
| --- | --- |
| Pilot module (validation) | $29/seat |
| Full curriculum — per seat | $59/seat |
| Facility license (up to 50 seats) | $2,200/year |
| Department license (up to 150 seats + LMS) | $5,500/year |
| Enterprise (unlimited + SCORM + branding) | $15,000–$22,000/year |

Discount through added value, not price cuts. Year 2 renewal: 10% loyalty. Year 3+: 15%.

Q6 — Distribution Direct sales only for first 12 months. No platform listing (HealthStream, Relias) until 10+ paying clients and brand equity established. Platform partnerships take 6–18 months to negotiate and surrender 30–50% revenue plus client relationship control.

Q7 — Geographic Priority NY + CA primary, TX secondary, national for digital/LinkedIn outreach. NY September 2026 mandate is the ticking clock. California has had active mandates since 2020. Texas September 2024 mandate underway.

# Part 3: Course Architecture

Working title: Healthcare Guardian: The Self-Advocate Safety System On-screen presenter: Morgan Hayes (AI avatar, HeyGen) Curriculum architect / brand voice: Elias Reed

## Module Map

| # | Module Title | Focus | Length |
| --- | --- | --- | --- |
| 1 | The Landscape of Risk | WPV scope, who’s at risk, why you can’t rely on others first | 8–10 min |
| 2 | Reading the Room | Environmental awareness, venue mapping, barrier/distance, exits | 10–12 min |
| 3 | Pattern Recognition and Early Warning (PILOT) | Behavioral escalation patterns, pre-incident indicators, JACA model | 10–12 min |
| 4 | The Neuroscience of Fear | Freeze response, Flee > Alert > Fight hierarchy, stress inoculation | 8–10 min |
| 5 | The Voice Before the Violence | Verbal de-escalation, Verbal Judo framework, command presence | 10–12 min |
| 6 | Team Safety Dynamics | Non-verbal colleague communication, team protocols, never being isolated | 8–10 min |
| 7 | When Words Aren’t Enough | Last resort principles — scope subject to future legal review; excluded from digital launch | 10–12 min |
| 8 | After the Incident | Documentation, trauma response, culture of non-acceptance | 8 min |

Total curriculum: ~75–90 minutes across 8 modules Each module: 1 scenario vignette + 1 knowledge check (4–5 questions) + 1 key principle summary card Completion: Certificate with timestamp, learner name, course version, CEU credit (pending ANCC approval) Format: SCORM 1.2 required for enterprise LMS integration; xAPI adds value for larger health systems

# Part 4: Phase 2 Validation Plan

## Objective

Validate — with real market signal — that sufficient demand exists to justify building the full 8-module curriculum. Prove buyers will pay the target price. Convert at least one prospect to a paying pilot client.

This phase ends with a go/no-go decision on full curriculum development.

## 6-Week Execution Timeline

Week 0 (Pre-Launch): LLC formed, domain live (healthcareguardiantraining.com), landing page live, survey published (Typeform), CRM set up (HubSpot free), 60-contact list built (20 CNOs, 20 Risk Managers, 20 Education Directors — prioritized NY, CA, TX)

Week 1: CNO Touch 1 to 20 contacts. LinkedIn Post 1 (Problem Statement). LinkedIn Post 3 (NY Compliance) + DMs to NY contacts. Log all contacts in CRM.

Week 2: Risk Manager Touch 1. LinkedIn Post 2 (Freeze Response). Survey live + Post 7 (Survey Launch). CNO Touch 2 follow-ups. Survey link in all outreach going forward.

Week 3: Education Director Touch 1. Posts 4 + 5. Risk Manager Touch 2. First survey data review. Respond personally to every reply — these are sales conversations.

Week 4: Posts 6 + 8. Education Director Touch 2. All Touch 3 closes. Any interested contacts should be scheduling discovery calls.

Week 5: Pilot offer push to all warm contacts (replied, clicked, or completed survey). Personal, non-automated email. Track: How many accept? How many ask pricing?

Week 6: Survey closed and analyzed. CRM reviewed. Go/no-go assessment. Phase 2 debrief written.

## Contact List Build (No Paid Tools Required)

- LinkedIn Sales Navigator free trial: “Chief Nursing Officer” + “New York” + “Hospital”

- Repeat for Risk Manager and Education Director in CA and TX

- American Hospital Association member directory (public)

- State hospital association directories (NY, CA, TX — all publish member lists)

Do not buy a list from a data broker for validation. 60 highly targeted contacts will produce more signal than 600 generic ones.

## Go / No-Go KPIs

| Signal | Green | Yellow | Red |
| --- | --- | --- | --- |
| Survey response rate | >10% | 5–10% | <5% |
| Outreach reply rate (all sequences) | >8% | 4–8% | <4% |
| Discovery calls booked from outreach | >10 | 5–10 | <5 |
| Survey Q8: current training rating avg | <3.5 | 3.5–4.0 | >4.0 |
| Survey Q16: WTP $40+/seat | >50% | 30–50% | <30% |
| Pilot module acceptances | >5 | 2–5 | 0–1 |
| Any paid pilot purchase ($29+) | 1+ | — | 0 |

Green on 5+ signals: Full curriculum build approved. Begin Phase 3. Yellow on 3+ signals: Identify weak signals. Adjust positioning or persona. 30-day extension. Red on 3+ signals: Do not proceed. Investigate root cause before spending another dollar.

## Phase 2 Cost Estimate

| Item | Cost |
| --- | --- |
| Domain (healthcareguardiantraining.com) | ~$15/year |
| Website (Carrd or Webflow basic) | $0–$19/month |
| Typeform (survey) | $0–$25/month |
| HubSpot CRM | $0 (free tier) |
| LinkedIn outreach | $0 (organic only) |
| Total Phase 2 | $15–$75 for 6 weeks |

# Part 5: Discovery Call Script

Use as a guide, not a script to read verbatim. Listen more than you talk.

Opening: “Thanks for connecting. I’ll keep this focused — I know your time is limited. I’ve been building Healthcare Guardian and I’m trying to make sure the program solves a real problem before I ask anyone to invest in it. I’d genuinely like to hear your perspective on what’s actually missing in your current training, if anything.”

Core Questions:

- “Walk me through what your current WPV training looks like — frequency, format, who delivers it.”

- “What does your staff tell you about it — does it stick? Do they feel better prepared after?”

- “If you could change one thing about how your organization approaches this, what would it be?”

- “Is this on your radar as a compliance issue right now, or a staff safety culture issue — or both?”

- “If I told you there was a program your staff could complete in under 90 minutes, that they’d actually retain, and that produces the documentation trail you need — what would that be worth annually?”

The Ask: “I’d like to offer you complimentary access to our pilot module — a complete 10-minute module on behavioral pattern recognition. You can assign it to a small group and give me honest feedback on whether it’s the right level for your team. No purchase required. Would that be useful?”

Strong Demand Signals: - Asks about pricing without being prompted - Mentions a specific incident or recent pattern - References a mandate or compliance deadline - Mentions budget authority

# Part 6: Demo Flow Summary (20-Minute Call)

| Phase | Time | Goal |
| --- | --- | --- |
| The Hook | 2 min | Get them talking about their reality before you pitch anything |
| The Problem Frame | 3 min | 3 stats; end with the “checkbox training” critique |
| Live Module Demo | 8 min | Morgan Hayes intro → escalation sequence → knowledge check → certificate |
| Objection Handling | 3 min | See below |
| The Close | 2 min | Enrollment link or specific next action — never “I’ll think about it” |

Key Objection Responses:

“We already have WPV training.” → “This isn’t a replacement — it’s a layer. What does your current program teach staff to do in the 30 seconds before a situation peaks?”

“No time for more training.” → “Module 3 is 12 minutes. Self-paced. Done between patients on a tablet.”

“Need to go through procurement.” → “The pilot bypasses that. $145 direct purchase. You can have data to bring to procurement next week.”

“What’s the ROI?” → “One nurse turnover event costs $40,000–$60,000. De-escalation training reduces incidents 40–60%. The pilot is $145.”

# Part 7: Evaluation Findings

## What’s Built and Ready

| Asset | Status |
| --- | --- |
| Phase 1 Market Research | ✅ Complete — solid, data-grounded |
| Phase 2 Validation Plan | ✅ Complete — structured with KPIs and go/no-go criteria |
| Expert recommendations on all 7 decisions | ✅ Complete |
| Outreach email sequences (3 personas × 3 touches) | ✅ Complete |
| LinkedIn content calendar (8 posts) | ✅ Complete |
| Module 3 HeyGen script (pilot module) | ✅ Complete |
| Module 3 production script + storyboard | ✅ Complete |
| Module 1 HeyGen script + production script | ✅ Complete |
| Pilot demo flow document | ✅ Complete |
| Landing page / website copy | ✅ Complete |
| Survey (Typeform or similar) | ✅ Complete |
| LinkedIn profile — Elias Reed | ✅ Complete |
| LLC Operating Agreement | ✅ Complete (template) |
| Mercury bank application guide | ✅ Complete |
| Stripe setup checklist | ✅ Complete |

## What Still Needs to Happen

| Task | Priority | Notes |
| --- | --- | --- |
| Fix email deliverability / sender identity | 🔴 Critical | Outreach emails flagging as spam; domain authentication (SPF/DKIM/DMARC) needed |
| Form Healthcare Guardian LLC in Arizona | 🔴 Critical | Must happen before any payment accepted |
| Open Mercury business bank account | 🔴 High | Depends on LLC + EIN |
| Set up Stripe under LLC | 🔴 High | Depends on LLC + bank |
| Build NY + CA contact list | 🔴 High | Current list was AZ-heavy — misaligned with validated strategy |
| Launch Phase 2 outreach | 🔴 High | Everything is built; nothing has been sent |
| Produce Module 3 in HeyGen | 🟡 Medium | Script complete; production not started |
| Teachable or TalentLMS account setup | 🟡 Medium | Needed to host pilot module |
| ANCC CEU accreditation application | 🟢 Later | Needed before enterprise sales; not blocking pilot |
| Legal review of curriculum | 🟢 Later | Budget $2,000–$5,000; needed before full launch |

## Flags and Risks

Geographic strategy deviation (Flag) The Phase 2 plan validated NY + CA as primary markets. The Arizona-focused outreach list (Banner Health, HonorHealth, Dignity Health, Carondelet) is a deviation. Arizona has no active WPV mandate. New York hospitals have a September 2026 deadline and are actively looking for solutions right now. The next outreach wave should correct this.

Email deliverability (Critical Blocker) Cold outreach from elias@healthcareguardiantraining.com is flagging as spam. Without domain authentication (SPF, DKIM, DMARC records), a properly warmed sending domain, and a clean IP, open rates will be below 10% regardless of copy quality. This must be fixed before any outreach is sent.

Physical content liability (Managed, not eliminated) Decision to exclude physical defense content from digital product is correct. Risk is not zero — even the behavioral content should have legal review before enterprise sales begin. Budget for this in Phase 3.

Validation vs. confirmation bias Positive survey responses are not paid transactions. The only hard validation signal is a paid purchase, even at $29. Separate soft interest from real demand in the tracking.

Discovery call exposure Elias Reed cannot be on a live voice call. The pilot demo flow describes a 20-minute discovery call but doesn’t specify who runs it. This gap needs a decision: use the self-serve flow only, hire a fractional SDR, or reconsider the real-identity vs. persona structure for call scenarios.

## Financial Picture

Phase 2 cost: $15–$75 (near-zero) Phase 3 (pilot production) cost: ~$500–$2,000 (HeyGen + platform setup) Full launch cost: $5,000–$12,000 (legal review, SCORM build, LMS, branding)

Break-even scenarios: - 3 Facility licenses @ $2,200/yr = $6,600 — covers monthly ops - 10 Facility licenses = $22,000/yr — validates demand, cash-flow positive - 5 Department licenses @ $5,500/yr = $27,500/yr — strong early traction

# Part 8: Recommended Next Actions (Prioritized)

- Fix email deliverability. Set SPF, DKIM, and DMARC on healthcareguardiantraining.com. Use a warm sending tool (Instantly, Lemlist, or Mailshake) before any outreach goes out.

- File Healthcare Guardian LLC in Arizona. $50–$85 at azcc.gov. Get EIN. Open Mercury account. Set up Stripe. This is a precondition for receiving any payment.

- Rebuild the outreach contact list targeting NY and CA. 20 CNOs, 20 Risk Managers, 20 Education Directors — all New York and California institutions first. Use LinkedIn Sales Navigator free trial + AHA and state hospital association directories. Do not purchase a list.

- Decide on the discovery call problem. Who runs live calls if they’re needed? Options: (a) self-serve only for the pilot, no live calls required; (b) Alistair runs calls under the Elias persona via voice-masked or text-only channel; (c) fractional SDR hired after first paid client.

- Launch Phase 2 outreach. Everything is built. Sequences are written. Survey is ready. Once deliverability is fixed and the list is rebuilt toward NY/CA, the clock starts.

- Produce Module 3 in HeyGen. Script is complete. Production takes a few hours once you’re in the platform. This is needed for the warm outreach pilot offer in Week 5.

# Appendix: Pricing Reference

| Tier | Price | Target |
| --- | --- | --- |
| Pilot module (per seat) | $29 | Validation pricing |
| Full curriculum (per seat) | $59 | Small practices, solo buyers |
| Facility annual license (50 seats) | $2,200/yr | Small hospitals, clinics |
| Department annual license (150 seats + LMS) | $5,500/yr | Hospital departments |
| Enterprise (unlimited + SCORM + branding) | $15,000–$22,000/yr | Health systems, multi-site |
| White label | $35,000–$75,000 + royalty | Large systems, associations |

Evaluation prepared by Woz — based on full review of 24 Healthcare Guardian source documents. All findings reflect document content as of March 2026. No external research conducted.